## Product Backlog
Sprint # | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
1 | 1 | 1 | As a developer, I want to set up the project infrastructure, so that I can begin building the system. | Must-have | - | Rachith S | Completed
1 | 1 | 2 | As a developer, I want to train the team on LLM-driven categorization and tagging, so that we understand the workflows. | Must-have | 1 | Rachith S | Completed
1 | 1 | 3 | As a developer, I want to collect and preprocess historical ticket data, so that the model has input for training. | Must-have | 2 | Rachith S | Completed
2 | 2 | 4 | As a developer, I want to use LLMs to automatically classify support documents, so that the knowledge base is well-organized. | Must-have | 3 | Rachith S | Completed
2 | 2 | 5 | As a developer, I want to validate the quality of the tags and categories, so that the classification is accurate. | Should-have | 4 | Rachith S | Completed
3 | 3 | 6 | As a developer, I want to implement a live recommendation model that suggests articles in real-time, so that agents get quick solutions. | Must-have | 5 | Rachith S | Completed
3 | 3 | 7 | As a developer, I want to track article usage to identify potential knowledge gaps, so that the knowledge base can be improved. | Must-have | 6 | Rachith S | Completed
3 | 3 | 8 | As a developer, I want to set up automated alerts for underrepresented topics, so that content managers are notified. | Should-have | 7 | Rachith S | Completed
4 | 4 | 9 | As a developer, I want to build and deploy analytics dashboards, so that we can visualize knowledge base health. | Must-have | 8 | Rachith S | Completed
4 | 4 | 10 | As a developer, I want to integrate Slack notifications for flagged content gaps, so that the team is kept up to date. | Should-have | 9 | Rachith S | Completed
4 | 4 | 11 | As a developer, I want to finalize the agent interfaces, so that agents can easily interact with the knowledge system. | Must-have | 10 | Rachith S | Completed

## Sprint 1 Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate (in hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1 | 1.1 | Define and set up Python environment and required libraries. | Aug 18th | Aug 18th | Rachith S | Coding | 3-Completed | 4 | Day 1: 4
| 1.2 | Set up Google Sheets API integration for data handling. | Aug 19th | Aug 19th | Rachith S | Coding | 3-Completed | 6 | Day 2: 6
2 | 2.1 | Research and select appropriate LLMs (GPT, LLaMA) for the project. | Aug 20th | Aug 20th | Rachith S | Research | 3-Completed | 4 | Day 3: 4
| 2.2 | Train the team on basic LLM workflows and best practices. | Aug 20th | Aug 21st | Rachith S | Meeting | 3-Completed | 2 | Day 4: 2
3 | 3.1 | Connect to the source of historical ticket data. | Aug 21st | Aug 22nd | Rachith S | Coding | 3-Completed | 8 | Day 5: 8
| 3.2 | Write scripts for data cleaning and preprocessing. | Aug 22nd | Aug 25th | Rachith S | Coding | 3-Completed | 10 | Day 6: 5; Day 7: 5
| 3.3 | Load preprocessed data into Google Sheets for model input. | Aug 26th | Aug 27th | Rachith S | Coding | 3-Completed | 6 | Day 8: 6

## Stand-up Meeting
Sprint | Day | Impediments | Action Taken
1 | Aug 18th | Guidelines to begin working on the model. | Begin the work.
1 | Aug 25th | Discussing outcomes from Sprint 1 (Milestone 1). | Make corrections to the model and begin UI work for Milestone 2.
2 | Sep 1st | Discussing outcomes from Sprint 2 (Milestone 2). | Make corrections to the UI. Start work on RAG system.
3 | Sep 8th | Discussing previous sprint outcome and discuss goals for the dashboard. | Make correction to the RAG system.
3 | Sep 15th | Finalize on the final UI and make any required corrections. | Make final changes and corrections.

## Retrospection
Sl. # | Sprint # | Sprint start date | Sprint end date | Team member | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | Aug 18th | Aug 29th | Rachith S | Code for the model. | Relying on hardcoded data. | Developing the UI. | Completed
2 | 2 | Sep 1st | Sep 12th | Rachith S | UI for booking and model. | Making changes to the model. | Developing the UI. | Completed
3 | 3 | Sep 15th | Sep 26th | Rachith S | Building the RAG system. | Code for RAG model. | Developing the UI. | Completed
4 | 4 | Sep 29th | Oct 3rd | Rachith S | Exploring data for dashboard. | Building the RAG system. | Developing the UI. | Completed
5 | 5 | Oct 6th | Oct 17th | Rachith S | Building the dashboard into the UI. | Exploring data for dashboards. | Developing the dashboards. | Completed